Project Management Processes
1.
Determine the Input, Process and Exit
criteria for each of the project management processes

Phases	Entry Criteria	Process	Exit Criteria
Project Initiation	A Business case based on a Problem or an Opportunity	Develop a business case / Undertake a feasibility study / Establish the Project Charter / Appoint the project team / Set up Project Office / Perform a Phase Review	Project Charter / Scope Staement
Project Planning	Project Charter / Scope Staement	Create a Project Plan / Create a Resource Plan / Create a Financial Plan / Create a Quality Plan / Create a Risk Plan / Create an Acceptance Plan / Create a CommunicationPlan / Create a Procurement Plan / Contract theProject Management Plan / Management plans for each Functional area / Ongoing Project plan Updates Suppliers / Perform a Phase Review	Project Management Plan / Management plans for each Functional area / Ongoing Project plan Updates
Project Execution	Project Management Plan / Management plans for each Functional area / Ongoing Project plan Updates	Perform Time Management / Perform Cost Management / Perform Quality Management / Perform Change Management / Perform Risk Management / Perform Issue Management / Perform Procurement Management / Perform Acceptance Management / Perform Communications Management / Perform a Phase Review	Project Deliverables / Change Managment Document / Performance baselines
Project Monitoring and Controlling	Project Deliverables / Change Managment Document / Performance baselines	regular reviews using WBS as basis / regular review of actual costs,risks resource loadings etc. / regular meetings / production of periodic progress reports / inspections/ audits	Progress and Status reports. / Plan Updates / Change requests / Work products/ Deliverables
Project Closure	Project Charter / Scope Staement / Project Management Plan / Management plans for each Functional area / Ongoing Project plan Updates / Project Deliverables / Change Managment Document / Performance baselines / Progress and Status reports. / Plan Updates / Change requests / Work products/ Deliverables	Obtaining acceptance by the customer or sponsor (approval to close) / Releasing people and resources / Reporting on team performance and lessons learned / Updating or finalizing documents, project records, and results / Finalizing procurements / Performing quality assurance activities / Storing or archiving information.	Certificate of completion / Staff work assignments / Plan updates / Final work products/deliverables or services